## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
e-Commerce website for online shopping
Group 35 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Keying Mo | Zhehan Wang | Jingyi Gu
Project Start Date: | 2021-09-14 |  |  |  |  | September | [20 empty] | October | [27 empty] | November
Scrolling Increment: | 0 | time axis 2021-09-14 to 2021-11-08
0
Milestone description | Category | Assigned to | Progress | Start | Days | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Iteration 01
Iteration planning and meeting | Goal | Keying Mo | 25% | 2021-09-14 | 2 | T: 2; W: 2
Complete stakeholder register | High Risk | Keying Mo | 95% | 2021-09-16 | 4
Design persona | Med Risk | Jingyi Gu | 75% | 2021-09-23 | 2
Review and test persona | Low Risk | Zhehang Wang | 35% | 2021-09-24 | 1
Complete prosses report | Med Risk | Jingyi Gu | 50% | 2021-09-30 | 3
Iterlation 02
Planning, estimating and scheduling | High Risk |  | 65% | 2021-10-12 | 2
Introduction to Github | Med Risk |  | 50% | 2021-10-14 | 4
Build software documentation | High Risk |  | 45% | 2021-10-19 | 2
Push new changes | High Risk |  | 75% | 2021-10-21 | 1
Iterlation 03
Governance&Risk Management | Med Risk |  | 50% | 2021-10-25 | 1
Risk Register | Med Risk |  | 65% | 2021-10-25 | 2
GitHub Forks and Pull requests | High Risk |  | 75% | 2021-10-28 | 3
Application of process improvement | Goal |  | 50% | 2021-11-02 | 1 | T: 2
GitHub pages | High Risk |  | 80% | 2021-11-02 | 4
Acceptance Testing | Med Risk |  | 60% | 2021-11-04 | 2
To add more data, Insert new rows ABOVE this one
Formulas:
Keying Mo = IFERROR(IF(MIN(Milestones4352[Start])=0,TODAY(),B11(Milestones4352[Start])),F12)

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-09 |  |  |  |  | November | [20 empty] | December
Scrolling Increment: | 1 | time axis 2021-11-10 to 2022-01-04
Milestone description | Category | Assigned to | Progress | Start | Days | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-09 | 3 | W: 2; T: 2
Task 2 | Milestone |  |  | 2021-11-14 | 1 | bar: S
Task 3 | Low Risk |  | 50% | 2021-11-06 | 10
Task 4 | Milestone |  |  | 2021-11-29 | 1 | bar: M
Task 5 | Med Risk |  | 10% | 2021-11-15 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-15 | 13
Task 2 | On Track |  | 50% | 2021-11-17 | 9
Task 3 | Low Risk |  | 33% | 2021-11-22 | 11
Task 4 | Milestone |  |  | 2021-11-24 | 1 | bar: W
Task 5 |  |  |  | 2021-11-25 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-24 | 4
Task 2 | Med Risk |  |  | 2021-11-27 | 14
Task 3 | On Track |  |  | 2021-12-12 | 6
Task 4 | Goal |  |  | 2021-12-16 | 3 | T: 2; F: 2; S: 2
Task 5 | Low Risk |  |  | 2021-11-15 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-19 | 15
Task 2 |  |  |  | 2022-01-02 | 5
Task 3 | Milestone |  |  | 2022-02-13 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-09 |  |  |  |  | November | [20 empty] | December | [27 empty] | January
Scrolling Increment: | 5 | time axis 2021-11-14 to 2022-01-08
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-11-14 to 2022-01-08
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-09 | 3
Task 2 | Milestone |  |  | 2021-11-14 | 1 | bar: 2021-11-14
Task 3 | Low Risk |  | 50% | 2021-11-06 | 10
Task 4 | Milestone |  |  | 2021-11-29 | 1 | bar: 2021-11-29
Task 5 | Med Risk |  | 10% | 2021-11-15 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-15 | 13
Task 2 | On Track |  | 50% | 2021-11-17 | 9
Task 3 | Low Risk |  | 33% | 2021-11-22 | 11
Task 4 | Milestone |  |  | 2021-11-24 | 1 | bar: 2021-11-24
Task 5 |  |  |  | 2021-11-25 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-24 | 4
Task 2 | Med Risk |  |  | 2021-11-27 | 14
Task 3 | On Track |  |  | 2021-12-12 | 6
Task 4 | Goal |  |  | 2021-12-16 | 3 | 2021-12-16: 2; 2021-12-17: 2; 2021-12-18: 2
Task 5 | Low Risk |  |  | 2021-11-15 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-19 | 15
Task 2 |  |  |  | 2022-01-02 | 5
Task 3 | Milestone |  |  | 2022-02-13 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one